## Sheet1
GROUP:8 -INDUSTRIAL INTERNSHIP LOGBOOK-SEMESTER-II
Sr no | Date | Enrollnment number | Names | Time | Daily Work Progress | week | weekly update
1 | 2022-08-08 | 21bt04001 | A Keerthana | 9:00am-12:00am | 9:00am-12:00am-Attended session by Amit Parmar sir
| (Monday) | 21bt04002 | Aditya Patel
|  | 21bt04023 | Vaidehi Gajjar | 1:00pm-3:00pm | Practical session held by Amit Parmar regarding bootstrap
|  | 21bt04027 | Prajwal Huggi |  | Disscussed about the goal of the website
|  | 21bt04030 | Jenil Shah |  | Made layout for the website-number and brief about the pages |  | Decided the topic for the website
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  |  |  | canteen management system
2 | 2022-08-10 | 21bt04001 | A Keerthana
| (Wednesday) | 21bt04002 | Aditya Patel |  | Whole team discussed about the details and features to be added in each sections |  | finalised the tools,framework and
|  | 21bt04023 | Vaidehi Gajjar | 9:00am-12:30 pm | of the websites , decided on what framework and tools will be used | week one | programming languages for the website
|  | 21bt04027 | Prajwal Huggi |  | (that is html ,css and javscript) |  | html,css and javascript
|  | 21bt04030 | Jenil Shah |  | Started learning and revising html and css taught
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  |  |  | started learning about application of
3 | 2022-08-12 | 21bt04001 | A Keerthana |  |  |  | languages
| (Friday) | 21bt04002 | Aditya Patel |  | Planned and finalised the final layout of the website
|  | 21bt04023 | Vaidehi Gajjar | 9:00am-12:00am | Further studied about html ,css and javascript applications
|  | 21bt04027 | Prajwal Huggi |  | Started making website home from scratch and linked html, css and javascript
|  | 21bt04030 | Jenil Shah
|  | 21bt04042 | Lakheda Jayprakash Bhavani
4 | 2022-08-16 | 21bt04001 | A Keerthana |  | Watched various videos and and looked into websites and themes to note
| (Tuesday) | 21bt04002 | Aditya Patel |  | the things we are going to include like header and its design,menu card design etc.
|  | 21bt04023 | Vaidehi Gajjar | 9:00am-12:00pm | Distributed work among our team that who will do what.
|  | 21bt04027 | Prajwal Huggi | 1:00pm-2:30pm | Gave a role and task to each member of the group
|  | 21bt04030 | Jenil Shah |  | (keerthana ,vaidehi, jenil-login page) |  | Did the sourcing of images
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  | (Jayprakash,Prajwal,Aditya- home page) |  | Looked into various websites for
5 | 2022-08-17 | 21bt04001 | A Keerthana | 9:00am-12:30pm | Made layout for the website login page and wrote basic html code added some |  | ideas regarding the theme,layout and
| (Wednesday) | 21bt04030 | Jenil Shah |  | styling to page, sourced images for the same |  | sections to b included
|  | 21bt04023 | Vaidehi Gajjar |  |  | week two
|  | 21bt04027 | Prajwal Huggi | 9:00am-12:30pm | Made layout for the website home page and wrote basic html code added some |  | Made separate login page and 2 variants
|  | 21bt04002 | Aditya Patel |  | styling to page, sourced images for the same |  | of home page and decided to merge its
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  |  |  | features later
6 | 2022-08-18 | 21bt04001 | A Keerthana | 9:00am-12:30 pm | Completed the website login page by improving and adding more styling.
| (Thursday) | 21bt04002 | Jenil Shah |  | Experimented and finalised the alignment of the page |  | completely styled and finished the
|  | 21bt04023 | Vaidehi Gajjar |  |  |  | login and home pages
|  | 21bt04027 | Prajwal Huggi | 9:00am-12:30pm | Completed the website home page by improving and adding more styling.
|  | 21bt04030 | Aditya Patel |  | Experimented and finalised the alignment of the page
|  | 21bt04042 | Lakheda Jayprakash Bhavani
7 | 2022-08-22 | 21bt04001 | A Keerthana | 9:00am-12:30pm | Tried linking pages together and saw videos and sources regarding the
| (monday) | 21bt04002 | Aditya Patel |  | same
|  | 21bt04023 | Vaidehi Gajjar | ABSENT
|  | 21bt04027 | Prajwal Huggi |  | worked on making menu card sample adding effects and styling, price to the same.
|  | 21bt04030 | Jenil Shah | 9:00am-12:30pm | Did image sourcing and saw various samples and sources to finalize the card
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  |  |  | Started making a new website from
8 | 2022-08-23 | 21bt04001 | A Keerthana | 9:00am-12:30pm | explored visual options and styles for different pages |  | scratch with various sections
|  | 21bt04002 | Aditya Patel
|  | 21bt04023 | Vaidehi Gajjar | ABSENT |  |  | made the basic layout of header,home
|  | 21bt04027 | Prajwal Huggi | 9:00am-12:30pm | Looked for ideas ,themes and videos for website |  | page,about us, menu section and top picks
|  | 21bt04030 | Jenil Shah |  | Came up with a new layout with fewer pages and with more sections
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  | Decided to start making website with new layout and design |  | Learnt javascript implemented
9 | 2022-08-24 | 21bt04001 | A Keerthana | 9:00am-12:30pm | made the header, added logo and various sections of pages |  | scroll up feature with it
|  | 21bt04002 | Aditya Patel |  | i.e made structure of header
|  | 21bt04023 | Vaidehi Gajjar | ABSENT |  | week three | saw videos and sources regarding the page
|  | 21bt04027 | Prajwal Huggi |  |  |  | visited food related website
|  | 21bt04030 | Jenil Shah | 9:00am-12:30pm | worked on home section and styled the aligned the header section
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  |  |  | tried to implement animated font
10 | 2022-08-25 | 21bt04001 | Vaidehi Gajjar | 9:00am-2:30 pm | Made the basic structure and styled the about us and top picks section which |  | and texts but that didn't work
|  | 21bt04002 | Jenil Shah |  | included the animation,various effects and logos
|  | 21bt04023 | A Keerthana |  | made the layout for the menu section saw various styles and themes for menu section |  | Added images and beautified the pages
|  | 21bt04027 | Prajwal Huggi | 9:30pm-12:30pm |  |  | made
|  | 21bt04030 | Aditya Patel
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  |  |  | Applied a animated image in home
11 | 2022-08-26 | 21bt04001 | Prajwal Huggi | 9:00am-12:30 pm | looked for ideas for scroll down page saw videos, options and sources |  | section
|  | 21bt04002 | Aditya Patel |  | in javascript for the same,completed the scroll down
|  | 21bt04023 | Vaidehi Gajjar
|  | 21bt04027 | A Keerthana |  | implemented the selected format and style and completed the menu section
|  | 21bt04030 | Jenil Shah
|  | 21bt04042 | Lakheda Jayprakash Bhavani
12 | 2022-08-29 | 21bt04001 | Prajwal Huggi | 09:00am-12:30pm | looked for ideas for loader page saw videos, options and sources
| (monday) | 21bt04002 | Aditya Patel |  | in javascript for the same,completed the loader page
|  | 21bt04023 | Vaidehi Gajjar | 9:30pm-12:30pm | made the layout for the review section saw various styles and themes for it
|  | 21bt04027 | A Keerthana
|  | 21bt04030 | Jenil Shah | 9:30pm-12:30pm | made the layout for the order section saw various styles and themes for it |  | Through javascript added loader
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  |  |  | page in the website with a gif
13 | 2022-08-30 | 21bt04001 | A Keerthana | ABSENT
|  | 21bt04002 | Aditya Patel | 9:30am-2:30pm | Made a cart with php and linked it with the website |  | Made layout and styling
|  | 21bt04023 | Vaidehi Gajjar | 9:30am-2:30pm | worked on the styling of the review and order section ,made and styled footer |  | of the review and order section
|  | 21bt04027 | Prajwal Huggi | ABSENT
|  | 21bt04030 | Jenil Shah | 9:30am-2:30pm | worked on the styling of the review and order section ,made and styled footer |  | Worked with php to make cart and link
|  | 21bt04042 | Lakheda Jayprakash Bhavani | ABSENT |  |  | it to the website created
14 | 2022-09-01 | 21bt04001 | A Keerthana | 9:00am-12:50pm | Attended session by Redspark regarding wordpress | week four
|  | 21bt04002 | Aditya Patel |  | improved cart and worked on the cart quantity feature in php |  | Gave final front-end finishes to the
|  | 21bt04023 | Vaidehi Gajjar | 1:30pm - 5pm | worked on the final front-end features in css added Carousel in the home section |  | whole website and made a footer too.
|  | 21bt04027 | Prajwal Huggi |  | worked on the cart quantity feature in php
|  | 21bt04030 | Jenil Shah |  | worked on the final front-end features in css added Carousel in the home section |  | Started with the report regarding the
|  | 21bt04042 | Lakheda Jayprakash Bhavani |  | worked on the final front-end features in css added Carousel in the home section |  | internship and completed it
15 | 2022-09-02 | 21bt04001 | A Keerthana |  | Completed the final report and website checked for the errors and responsiveness
|  | 21bt04002 | Aditya Patel | 9:00am-3:00pm | of the website
|  | 21bt04023 | Vaidehi Gajjar
|  | 21bt04027 | Prajwal Huggi
|  | 21bt04030 | Jenil Shah | 3:00pm onwards | Presentation of website and viva
|  | 21bt04042 | Lakheda Jayprakash Bhavani
|  | Group Number | Faculty Mentor | Group Members | Enrollnment Number | Website name | Website Topic
|  | 8 | Mrs Swati Saxena | A Keerthana | 21bt04001 | CanteenPoint | Canteen management website
|  |  |  | Aditya Patel | 21bt04002 |  | to make order before hand
|  |  |  | Vaidehi Gajjar | 21bt04023 |  | their break
|  |  |  | Prajwal Huggi | 21bt04027
|  |  |  | Jenil Shah | 21bt04030
|  |  |  | Jayprakash Lakheda | 21bt04042